# Business Plan - YallaRent

## 1. Executive Summary

### 1.1 Description

YallaRent is a student equipment rental and sharing platform for Algerian campuses. It combines: - Company-owned inventory rental, - Peer-to-peer student listings, - Campus-adjacent pickup/return hubs, - Optional delivery, protection, and maintenance services.

The model addresses temporary-use demand in a large university population (1,530,230 enrolled students in 2024/2025) S09.

### 1.2 Business Overview and Objectives

Business objective (5-year): build a pilot-proven, campus-scalable rental infrastructure with no commission on P2P transactions A28.

Primary objectives: 1. Pilot and validate unit economics in AY 2026/2027. 2. Reach operational break-even from Year 2 (base case) A27. 3. Expand from 1 campus to 18 campuses by Year 5 A06. 4. Build mixed revenue resilience across 7 streams A31 to A37.

### 1.3 Product and Value Proposition

For students: temporary access to essential equipment without heavy upfront purchase.

For student providers: monetization of idle assets with verification and trust tooling.

For universities: partner-ready service layer that improves student living support.

Digital channel feasibility is strong with 36.2 million internet users (76.9%) and 54.8 million mobile connections (116%) in early 2025 S16, S15.

### 1.4 Market and Customers

- TAM baseline: 1,530,230 enrolled students S09.

- Targeted initial SOM (active renters): 1,200 in AY 2026/2027 A07.

- Year-5 active renters target: 47,500 A07.

### 1.5 Strategy and Development

- Phase 1 (AY26/27): 1-campus pilot with controlled SKU scope.

- Phase 2 (AY27/28 to AY28/29): 3 to 7 campuses, stronger partner contracts.

- Phase 3 (AY29/30 to AY30/31): 12 to 18 campuses, full multi-stream model.

### 1.6 Financials and Resources (Base Case)

| Year | Revenue (DZD) | Operating Cost (DZD) | Operating Result (DZD) |
| --- | --- | --- | --- |
| AY26/27 | 21,593,600 | 25,800,000 | -4,206,400 |
| AY27/28 | 60,504,000 | 48,300,000 | 12,204,000 |
| AY28/29 | 132,507,200 | 83,000,000 | 49,507,200 |
| AY29/30 | 241,950,000 | 133,000,000 | 108,950,000 |
| AY30/31 | 388,190,000 | 201,300,000 | 186,890,000 |

(Model assumptions: A06 to A37)

### 1.7 Risks and Mitigation (Summary)

- Buyer price sensitivity under youth unemployment and inflation S06, S07.

- Substitute pressure from informal/classified channels S26, S27.

- Compliance obligations under Law 18-07 S22, S23.

## 2. Company Overview & Management

### 2.1 Company Description

YallaRent operates as a campus-focused rental operations platform with a hybrid physical-digital model.

### 2.2 Legal and Regulatory Position

- Startup policy path includes a 4-year renewable label framework S24, S25.

- Personal-data processing must align with Law 18-07 obligations, including consent logic S22, S23.

### 2.3 Management Structure (Planned)

- CEO: partnerships, growth, governance.

- COO: hubs, logistics, operations.

- CTO: platform, security, data governance.

- Trust & Safety Lead: verification, disputes, incident response.

- Finance Lead: budgeting, controls, scenario management.

### 2.4 HR Ramp (Base Case)

| Year | Core Team FTE |
| --- | --- |
| AY26/27 | 11 |
| AY27/28 | 18 |
| AY28/29 | 28 |
| AY29/30 | 40 |
| AY30/31 | 55 |

(Internal HR plan linked to cost growth assumptions A25, A26.)

## 3. Products / Services

### 3.1 Product Overview

- Company-owned item rentals.

- P2P listings (free up to 3 items, paid plans above threshold) A14, A28.

- Delivery and pickup options A10, A11.

- Damage protection add-on A12, A13.

- Maintenance and end-cycle resale A18 to A21.

### 3.2 Technical Characteristics and Quality

- Mobile-first UX required by local connectivity context S15, S16.

- Performance target informed by local median speeds (23.42 Mbps mobile; 15.05 Mbps fixed) S18, S19.

- Role-based admin controls and auditable event logs for trust and compliance.

### 3.3 Product Strengths and Competitive Advantages

- Campus-specific logistics workflow versus generic classified platforms S26, S27.

- Mixed revenue engine without P2P commission dependency A28.

- Built-in refurbishment/resale loop for inventory lifecycle control A20, A21.

### 3.4 Client Purchase Factors

- Total cost transparency.

- Trust in item condition and identity checks.

- Speed and convenience of handover.

- Availability at semester-critical dates.

### 3.5 Product Portfolio and Revenue Contribution (Base Case)

| Stream | AY26/27 Share | AY30/31 Share |
| --- | --- | --- |
| Company-owned rentals | 60.0% | 51.0% |
| Delivery fees | 3.5% | 4.1% |
| Damage protection | 3.6% | 4.5% |
| Subscription plans | 8.3% | 13.9% |
| University partnerships | 13.9% | 17.3% |
| Maintenance | 2.5% | 2.5% |
| Resale | 8.1% | 6.7% |

### 3.6 Product Development Roadmap

- Year 1: booking core, verification, hub workflow, basic provider dashboard.

- Year 2-3: automation for disputes, SLA dashboarding, improved provider controls.

- Year 4-5: cross-campus inventory optimization and advanced risk scoring.

### 3.7 Market Life Cycle and Seasonality

- Demand peaks around semester starts and exam windows.

- End-of-semester return cycles feed maintenance and resale channels.

### 3.8 Sales Projection Drivers

- Active renters growth A07.

- Orders and average fee growth A08, A09.

- Attach-rate progression A10, A12.

### 3.9 After-Sales Service and Support

- Return inspections and damage workflows.

- Maintenance interventions and replacement path.

- Escalation path for disputes.

## 4. Market & Clients

### 4.1 Market Sizing

- TAM: 1,530,230 enrolled students S09.

- SAM (internal launch focus): 382,558 students (25% of TAM) A02.

- SOM: starts at 1,200 active renters, scales to 47,500 by Year 5 A07.

### 4.2 Segment Prioritization

- Students in high-mobility housing patterns.

- Students with temporary semester needs.

- Student providers with idle assets.

### 4.3 Demand Conditions

- Affordability pressure: youth unemployment 29.444% S06.

- Stable digital readiness: 76.9% internet penetration S16.

### 4.4 Geographic Rollout Logic

- Start dense (one campus cluster), then expand by operating playbook replication.

- Higher education network scale (117 institutions) supports long runway S12.

## 5. Competition

### 5.1 Local Alternatives

- Ouedkniss: broad classified market S26.

- OpenSooq: furniture listing channel S27.

- Dirleco: local rental behavior proof in non-student equipment categories S28.

### 5.2 International Benchmarks

- CORT student package benchmark starts at $139 and references 12-month lease framing S29, S30.

### 5.3 Positioning

YallaRent differentiates on trust + campus logistics + mixed physical/digital service layer, not listing volume alone.

### 5.4 Competitive Response Plan

- Maintain no-commission P2P positioning.

- Expand defensibility through operational SLAs and partner density.

- Use bundle economics and lifecycle controls to protect margins.

## 6. Marketing Plan

### 6.1 Product Strategy

- Focus categories: study productivity and dorm comfort essentials.

- Build repeat behavior through bundles and semester-aligned offers.

### 6.2 Pricing Strategy

- Budget-sensitive architecture due unemployment/inflation environment S06, S07.

- Planned fee anchors:

  - Company-owned average order: 1,800 DZD (Y1), rising to 2,200 DZD (Y5) A09.

  - Delivery: 300 to 380 DZD A11.

  - Protection: 180 to 260 DZD A13.

  - Provider plan: 12,000 DZD annual A15.

### 6.3 Communication and Promotion Strategy

- Campus ambassadors and referral loops.

- Mobile-first growth channels aligned with 25.6M social identities S17.

- Trust-led messaging: verification, condition evidence, and safe returns.

### 6.4 Distribution Strategy

- Digital booking + physical hub fulfillment.

- Optional last-mile delivery for higher-convenience segments.

### 6.5 Growth KPIs

| KPI | Y1 Target | Y3 Target | Y5 Target |
| --- | --- | --- | --- |
| Active renters | 1,200 | 10,500 | 47,500 |
| Repeat rental rate | 30% | 42% | 52% |
| Provider paid-plan conversion | 12% | 18% | 24% |
| Dispute resolution within SLA | 85% | 92% | 95% |

(Targets from internal growth model A07, A14.)

## 7. Infrastructure & Technology

### 7.1 Platform Infrastructure

- Student interface: browse, reserve, manage rentals.

- Provider interface: list, approve, track earnings.

- Admin interface: verification, moderation, disputes, quality controls.

### 7.2 Operations Infrastructure

- Hubs for pickup/return/inspection.

- Inventory tracking and condition history.

- Maintenance queue and repair workflow.

### 7.3 Sales and Administration

- Campus pipeline tracking.

- Partner contract lifecycle management.

- Centralized pricing and category management.

### 7.4 Premises and Physical Footprint

- Pilot uses light hub footprint.

- Scale stage adds capacity by campus based on utilization and order density A22.

## 8. Financial Management

### 8.1 Financial Objectives

- Reach annual operating break-even by AY27/28 in base case A27.

- Preserve liquidity buffer during pilot and rollout phases.

### 8.2 Monitoring System

Monthly review packs: - Revenue by stream, - Cost by function, - Utilization and damage KPIs, - Campus-level contribution margins.

### 8.3 Financial Tools and Controls

- Rolling 18-month cash planning.

- Scenario analysis (conservative/base/upside) A25, A26.

- Approval thresholds for capex and inventory purchases.

### 8.4 Governance and Responsibilities

- Finance lead owns reporting and forecast discipline.

- COO co-owns operational cost controls.

- CEO owns partner revenue targets.

### 8.5 Capital Structure and Financing Plan

- Pilot financed through founder capital + grant/competition pipeline.

- Expansion financing triggered after validated Year-2 economics.

## 9. Financial & Operational Planning

### 9.1 Base Case Revenue by Stream (DZD)

| Stream | AY26/27 | AY27/28 | AY28/29 | AY29/30 | AY30/31 |
| --- | --- | --- | --- | --- | --- |
| Company-owned rentals | 12,960,000 | 34,200,000 | 72,000,000 | 126,000,000 | 198,000,000 |
| Delivery fees | 756,000 | 2,304,000 | 5,140,800 | 9,720,000 | 16,074,000 |
| Damage protection | 777,600 | 2,340,000 | 5,306,400 | 10,080,000 | 17,316,000 |
| Provider subscriptions | 1,800,000 | 6,000,000 | 16,800,000 | 33,600,000 | 54,000,000 |
| University partnerships | 3,000,000 | 9,000,000 | 20,000,000 | 39,600,000 | 67,200,000 |
| Maintenance services | 540,000 | 1,560,000 | 3,360,000 | 5,850,000 | 9,600,000 |
| End-cycle resale | 1,760,000 | 5,100,000 | 9,900,000 | 17,100,000 | 26,000,000 |
| Total Revenue | 21,593,600 | 60,504,000 | 132,507,200 | 241,950,000 | 388,190,000 |

### 9.2 Base Case Operating Cost Plan (DZD)

| Cost Category | AY26/27 | AY27/28 | AY28/29 | AY29/30 | AY30/31 |
| --- | --- | --- | --- | --- | --- |
| Inventory procurement & refurbishment | 7,200,000 | 16,000,000 | 31,000,000 | 52,000,000 | 81,000,000 |
| Hub operations & storage | 2,400,000 | 5,000,000 | 9,000,000 | 15,000,000 | 24,000,000 |
| Payroll | 9,600,000 | 14,000,000 | 21,000,000 | 31,000,000 | 44,000,000 |
| Technology / cloud / payments | 1,800,000 | 3,000,000 | 4,800,000 | 7,000,000 | 9,800,000 |
| Marketing & sales | 2,200,000 | 5,000,000 | 9,000,000 | 15,000,000 | 23,000,000 |
| Maintenance operations | 1,100,000 | 2,500,000 | 4,000,000 | 6,500,000 | 10,000,000 |
| G&A / legal / compliance | 1,500,000 | 2,800,000 | 4,200,000 | 6,500,000 | 9,500,000 |
| Total Operating Cost | 25,800,000 | 48,300,000 | 83,000,000 | 133,000,000 | 201,300,000 |

### 9.3 Operating Result (Base Case)

| Year | Revenue | Cost | Operating Result |
| --- | --- | --- | --- |
| AY26/27 | 21,593,600 | 25,800,000 | -4,206,400 |
| AY27/28 | 60,504,000 | 48,300,000 | 12,204,000 |
| AY28/29 | 132,507,200 | 83,000,000 | 49,507,200 |
| AY29/30 | 241,950,000 | 133,000,000 | 108,950,000 |
| AY30/31 | 388,190,000 | 201,300,000 | 186,890,000 |

### 9.4 Scenario View (Conservative / Base / Upside)

Scenario rules: revenue and cost multipliers from A25 and A26.

| Year | Conservative Result | Base Result | Upside Result |
| --- | --- | --- | --- |
| AY26/27 | -6,461,120 | -4,206,400 | -1,388,000 |
| AY27/28 | 3,967,200 | 12,204,000 | 22,500,000 |
| AY28/29 | 29,645,760 | 49,507,200 | 74,334,000 |
| AY29/30 | 71,200,000 | 108,950,000 | 156,137,500 |
| AY30/31 | 125,356,000 | 186,890,000 | 263,807,500 |

### 9.5 Break-Even

- Base-case annual break-even is reached in AY27/28 A27.

- Cumulative break-even (covering initial Year-1 deficit) is reached during AY27/28.

### 9.6 Sensitivity Highlights

| Driver | Low Case | Base | High Case | Impact Summary |
| --- | --- | --- | --- | --- |
| Utilization rate | 48% | 58% | 68% | Approx. +/- 14% impact on company-owned rental revenue A22. |
| Non-recoverable damage rate | 4.0% | 2.8% | 2.0% | Approx. -/+ 3 to 5 points on operating margin A23. |
| Campus acquisition pace | -1 campus/year from Y2 | Base | +1 campus/year from Y2 | Directly shifts Y5 revenue by ~15-20% in model envelope A24. |

### 9.7 Financing Strategy

- Prioritize low-dilution pilot capital until Year-2 proof.

- Fund expansion hubs after repeatability metrics are stable.

### 9.8 Three Best-Performing Products (Expected by Revenue)

- Company-owned rentals A31

- University partnerships A35

- Provider subscriptions A34

### 9.9 Top Three Client Buckets in Forecast

- Student renters in core campus clusters.

- Student providers with paid listing plans.

- University partner accounts.

### 9.10 Seasonal Cash-Flow Considerations

- Upfront inventory and setup spend before semester starts.

- Mid-semester utilization peak improves cash generation.

- End-of-semester returns drive maintenance and resale cash events.

### 9.11 Financing New Acquisitions

- Inventory acquisition cadence tied to utilization and return-cycle analytics.

- Procurement cap tied to maintained liquidity thresholds.

## 10. Risk Assessment

### 10.1 Internal Risks (Organization, Management, Operations)

- Early-stage execution overload across logistics and support.

- Mitigation: phased campus expansion and SLA-led operating cadence.

### 10.2 Commercial Risks (Market, Product, Pricing)

- Strong substitute pressure from informal/classified channels S26, S27.

- Mitigation: trust differentiation and bundle economics.

### 10.3 Financial Risks

- Inflation and cost drift S07.

- Mitigation: quarterly repricing controls and scenario re-forecasting.

### 10.4 Exogenous Risks (Legal, Political)

- Data-governance failures can create legal exposure under Law 18-07 S22, S23.

- Mitigation: consent and retention governance by design.

### 10.5 Technical and Operational Risks

- Device/network heterogeneity despite improving speed trends S18, S20.

- Mitigation: mobile performance budget and fallback flows.

### 10.6 Environmental and Ecological Risks

- High damage rates weaken resale sustainability loop.

- Mitigation: inspection protocol + maintenance routing + quality scorecards.

### 10.7 Risk Probability-Impact Matrix (Summary)

| Risk | Probability | Impact | Priority |
| --- | --- | --- | --- |
| Low adoption vs. target | Medium | High | High |
| High damage/loss rate | Medium | High | High |
| Compliance incident | Low-Medium | High | High |
| Supply stockout peak | Medium | Medium | Medium |
| Logistics SLA misses | Medium | Medium | Medium |

### 10.8 Risk Management Philosophy

Operate with conservative pilot controls, data-backed scaling gates, and quarterly scenario recalibration.

## 11. Appendices

### 11.1 Linked Supporting Documents

- Porter 5+1

- Empathy Card

- PESTEL Analysis

- Business Model Canvas

- Services Overview

- Assumptions Register

- Source Register

- Glossary

### 11.2 Source Quality Notes

- Priority given to official/public-primary sources for demographics, macroeconomics, education, and legal context.

- Industry source (DataReportal) used for digital adoption and speed metrics where official dashboards are less operationally specific.

- Company-primary pages used for competitor existence and benchmark positioning.